Phase 1: Preparation & Stakeholder Identification (Months 1–2, Typically starts in May or June)

The goal of this phase is to ensure a highly participative and collaborative process involving all key constituencies.

- Month 1: Form the Strategic Planning Committee

- Identify and recruit representatives from the administration, faculty, staff, parents, and board members.

- Notify the Assistant Superintendent for Research and Planning.

- Deliverable: Defined roles and responsibilities for the planning committee.

- Month 2: Stakeholder Engagement Launch

- Launch an initial survey for parents to gather a baseline for satisfaction and actionable insights.

- Conduct town halls or focus groups with faculty and staff to discuss the school's philosophy and mission.

Phase 2: Assessment & Foundation Building (Months 3–4, Typically starts in July or August)

This phase focuses on a "mission-driven" evaluation of the school’s current state.

- Month 3: SWOT Analysis

- Conduct a formal evaluation of strengths, weaknesses, opportunities, and threats (SWOT).

- Analyze data points including enrollment numbers, academic performance, financial stability, and fidelity to the Catholic mission.

- Month 4: Mission and Vision Affirmation

- Review and, if necessary, update the Mission Statement, Vision Statement, and Core Values.

- Ensure these foundational elements animate daily actions and serve as the cornerstone for the five pillars.

Phase 3: Pillar Development & Goal Setting (Months 5–7, Typically starts in September or October)

Drafting the specific strategic initiatives for each of the five pillars.

- Month 5: Pillars I & II (Catholic Identity and Academic Excellence)

- Draft goals for deepening the integration of mission and enhancing faith formation.

- Develop plans for curriculum alignment and Professional Learning Communities (PLCs) for faculty.

- Month 6: Pillars III & IV (Operational Vitality and Governance)

- Develop a 3-5 year financial plan and define the tuition philosophy (e.g., actual cost-per-pupil vs. market-driven).

- Draft a leadership succession plan and define board oversight roles.

- Month 7: Pillar V (Strategic Action Plan)

- Translate all goals into Key Action Steps with assigned Responsible Parties and KPIs.

Phase 4: Finalization & Communication (Months 8–9, Typically starts in November or December)

Ensuring the plan is ready for implementation and transparently shared.

- Month 8: Review and Approval

- Conduct a final review with the governing body and CSO.

- Ensure the budget aligns financial resources with these new strategic priorities.

- Month 9: Launch and Annual Report Setup

- Publish the comprehensive Annual Report to all constituencies.

- Execute the communication plan to provide transparent updates on the plan's implementation.